## Onboarding Project Overview
Blumira Onboarding Project Plan
Contacts | Blumira | Name: MSP Team Contact: msp@blumira.com Meeting Link: https://blumirapartners.zendesk.com/hc/en-us/articles/6467463924755 | Customer | Company Name: Name: [customer name] Title: [title]
Onboarding Progress
About Stages and Onboarding:
This document aims to describe and lay out the plan for your onboarding with Blumira. Some of these steps can be completed prior to your first meeting with your assigned Technical Account Manager (TAM). However, we will still lay out plans and detail these items in order to better track your progress as we move through your onboarding. We are so excited that you’ve decided to partner with Blumira and we are looking forward to working with you!
Stage |  | Description
Phase 1: Discovery and Documentation |  | This phase is designed to help us find what needs to be logged in your environment and to track these items. Also, this phase is used to perform a knowledge transfer so you have the documentation you need to implement configurations.
Phase 2: Configurations |  | This phase is where we will start running through the implementation of logging configurations. As your Technical Account Manager, my duty is to make sure that you have all the knowledge necessary to be able to implement logging configurations so we can have logs forwarded to the Blumira Platform. This phase will be a mixture of some time with me, to co-pilot a few configurations with you, and time for you and/or your team to configure remaining systems/integrations on your own.
Phase 3: Training & Final Steps |  | This phase is used to help train you and anyone else that will be logging in to the Blumira platform. We will go over several topics listed below and make sure you feel comfortable within the app. We will also detail the paths for getting help when you need it. Afterwards, you will receive a copy of this onboarding sheet for your records.
Phase 4: Post-Onboarding Check In |  | This last phase is designed for us, as your TAM, to check in with you after completing the onboarding. During this check in we will review all the integrations you’ve configured and validate that no remediations are necessary. We will also conduct a Shodan scan/search and validate with you that there are no coverage gaps in your logging configurations. This is also a good time to bring up questions to us that you’ve developed during your time with the product since onboarding.

## Discovery Questions
Question | Answer
Where is your infrastructure located? Examples: Ann Arbor, MI or Azure Cloud - Central Region
What is your public address space? Examples: CIDR addresses such as 1.2.3.0/24, 2.3.4.5/28, 3.4.5.6/32 or individual IPs 4.5.6.7, 6.7.8.9
Which cloud-based services do you use, if any? Examples: o365, LastPass, Okta, Duo
Which types of networking infrastructure do you use? Examples: Cisco ASA w/FirePower Module, Palo Alto Firewalls, Meraki Wireless
Which server OSes and versions do you use, and how many of each do you have? Examples: 25 - Windows Server 2016, 42 - Windows Server 2019, 10 - Ubuntu Linux v18
Which EDR, XDR, and AV endpoint solutions do you use? Example: Trend Micro Apex One, Carbon Black Defense, Microsoft Defender for Identity
Which RMM or automation tooling do you use? Example: CW Automate, PDQ Deploy, NinjaOne
Do you have cybersecurity insurance?
Do you have an incident response (IR) vendor and/or does your cybersecurity insurance company require that you use a specific IR vendor?
If you have an IR vendor or your cybersecurity insurance requires that you use a specific IR vendor, what is their name?
What did we miss? Please add details of application or infrastructure items that were not listed above. Example: Exchange On-Prem (with OWA), IIS, Apache, Nessus Security Scanner

## Onboarding Checklist
Phase | Task/Item | Status
Phase 1 & 2 Discovery and Configurations | Discovery Questions Completed | TRUE | Inventory | Completed | Coverage Gap | Percent Covered
| Cloud Apps | FALSE | 1 | 0 | 100% | 0%
| Network Infrastructure | FALSE | 1 | 0 | 100% | 0%
| Server Infrastructure | FALSE | 1 | 0 | 100% | 0%
| Endpoints | FALSE | 1 | 0 | 100% | 0%
| Public CIDR | FALSE | Additional Data for Tables
| Cyber Security Insurance Check | FALSE
| IR Company | FALSE | Task Count | 37
Phase 3 Training | Summary Page | FALSE | Completed | 1
| Findings Page | FALSE | Percent Completed | 2.703%
| Working Findings | FALSE | Post Task Count | 7
| • Message Field: SecOps and Support | FALSE | Completed | 0
| • Detection Filters | FALSE | Percent Completed | 0%
| • Matched Evidence Overview | FALSE
| Report Buiilder | FALSE
| • 7 Day Summary | FALSE
| • Sysmon Log Counts | FALSE
| • How to build and save custom reports | FALSE
| Scheduled Reports | FALSE
| • How to and walkthrough | FALSE
| Detection Rules | FALSE
| • Detection Filters | FALSE
| Blocklists and Threat Feeds | FALSE
| Cloud Connectors | FALSE
| Sensor Page | FALSE
| • Rebuilding | FALSE
| • Add, edit, and remove modules | FALSE
| • Logging devices table and how to | FALSE
| User & Notifications | FALSE
| • How to set and change notifications for yourself | FALSE
| • How to set and change notifications for others | FALSE
| • Resetting MFA | FALSE
| • Editing user details | FALSE
| Who/When/Why/How to contact TAM and SecOps/Support | FALSE
Final Steps | FR Discovery | FALSE
| • Are we missing anything the customer needs | FALSE
| Product Review Request | FALSE
| • Gartner | FALSE
| • G2 | FALSE
| • Capterra | FALSE
Check In Topics | Check-In Scheduling: | FALSE
| • MM/DD/YYYY | FALSE
| Review of Logging Coverage | FALSE
| • 7 Day Summary Reporting | FALSE
| FR Discovery | FALSE
| • Are we Missing anything the customer needs | FALSE
| External Threat Surface Scanning | FALSE
| • Shodan | FALSE

## Internal Onboarding Notes
Date (doubleclick cell for date picker) | Notes